## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
FIRST SEMESTER INTERDISCIPLINARY PROJECT
Plaza Hotel |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
by Bartosz Biryło & Octavian Roman
Project Start Date: | 2021-11-16 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 0 | time axis 2021-11-16 to 2022-01-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-16 to 2022-01-10
GITHUB SETUP
GitHub Organization | Low Risk | Bartosz | 100% | 2021-11-16 | 1
GitHub Repository | Low Risk | Bartosz | 100% | 2021-11-16 | 1
BUSINESS DIAGRAMS ELABORATION
Gantt Chart | Med Risk | Octavian | 100% | 2021-11-16 | 3
Stakeholder Analysis | Low Risk | Octavian | 100% | 2021-11-18 | 3
Business Model Canvas | Low Risk | Octavian | 100% | 2021-11-17 | 2
SWOT Analysis | Low Risk | Octavian | 100% | 2021-11-16 | 1
SOFTWARE DEVELOPMENT DIAGRAMS ELABORATION
Four Use Cases | Low Risk | Octavian | 100% | 2021-11-18 | 1
Use Case Descriptions | Low Risk | Octavian | 100% | 2021-11-18 | 2
Use Case Model | Med Risk | Octavian | 100% | 2021-11-18 | 6
Domain Model | Med Risk | Octavian | 100% | 2021-11-18 | 4
System Sequence Diagram | Med Risk | Octavian | 100% | 2021-11-19 | 1
Sequence Diagram | Low Risk | Octavian | 1000% | 2021-11-19 | 1
Class Diagram | High Risk | Both | 100% | 2021-11-20 | 13
SOURCE CODE DEVELOPMENT
"Item" Class | High Risk | Bartosz | 100% | 2021-11-20 | 6
"Guest" Class | High Risk | Bartosz | 100% | 2021-11-20 | 13
"Room" Class | High Risk | Bartosz | 100% | 2021-11-20 | 13
"Staff" Class | High Risk | Octavian | 100% | 2021-11-20 | 13
"Bookings" Class | High Risk | Octavian | 100% | 2021-11-20 | 13
"Authentication" Class | High Risk | Octavian | 100% | 2021-11-20 | 10
"User" Class | High Risk | Octavian | 100% | 2021-11-20 | 7
"UI" Class | High Risk | Both | 100% | 2021-11-20 | 13
"Database" Class | High Risk | Bartosz | 100% | 2021-11-20 | 13
"Main" Class | High Risk | Both | 100% | 2021-11-20 | 13
PRESENTATION PREPARATION & CREATION
PowerPoint Presentation | Med Risk | Octavian | 100% | 2021-12-03 | 2
Presentation Role Assignment | Med Risk | Octavian | 100% | 2021-12-03 | 2
To add more data, Insert new rows ABOVE this one